## Sheet1
Preparing for the Electronic Prescription Service
Nomination | Done
Familiarise yourself with the PCT Nomination Policy
Ensure Standard Opertating Procedures are updated/in place
Consider how you will promote EPS Release 2 to your patients (posters, leaflets etc.)
Collect patient nominations
Ensure a supply of nomination forms is available
Update Standard Operating Procedures (SOPs) | Done
Business continuity
Nomination, including process to store nomination forms
Dispensing
Accuracy checking
Smartcards
Claiming
Complaints
EPS Release 2 Training | Done
Ensure all staff are aware of the EPS Release 2 and its functionality
Agree a training date with your system supplier
System training (including locums)
Business process training
Smartcards | Done
Ensure Sponsor/staff are aware of how to unlock Smartcards and re-issue certificates
All relevant staff have been issued Smartcards
Ensure staff know their account recovery password to enable Smartcard use
Ensure the mobile number is complete on each member of staff's Smartcard profile.
Return premises Smartcard to PCT (card with the green cross)
Check that EPS Release 2 Smartcards are working correctly for all staff
System | Done
Choose an EPS Release 2 system (consider your pharmacy workflow)
Order EPS Release 2 system
Agree go-live dates with your system supplier
Installation of EPS Release 2 system
Things to discuss with your system supplier | Done
Business Continuity
Consider your pharmacy's workflow (how many terminals, printers etc. will you need?)
How should incidents be raised?
Hardware/Software requirements
Training approach
Back-up/rollback plan
NCSOs
Discuss dossetts/MDS
Discuss management of prescriptions (housekeeping)
Using EPS Release 2
In Practice | Done
Submission of synthetic prescription to activate £1,000 payment
Check that your pharmacy is flagged as EPS R2 enabled on NHS Choices
Continue as per usual process until you receive your first EPS Release 2 prescription
Familiarise yourself with the claiming process for EPS Release 2
Ensure you are aware of the dispensing token ordering process
Continue to promote EPS Release 2 with your patients
Evaluate business processes
Nomination | Done
Continue to capture nominations
Preparation | Done
Ensure you have a supply of Dispensing Tokens
Update Locum Briefing Pack
Scan EPS Release 1 prescriptions to ensure patient details correct (this helps with setting nominations)
Check that your pharmacy's details are correct on NHS Choices & register to edit details
Capture exemption details in system
Agree processes with local GPs (queries & cancellations, repeat dispensing, business continuity scenarios, split prescriptions)